## Sheet1
SPRINT 1
Task No | Task Name
1 | Project Proposal
2 | Participant recruitment
3 | Update proposal based on the feedback received from the critique
4 | Conduct literature survey on related projects
5 | Organise group
6 | Sprint 1: Collect raw data from test subjects
7 | Sprint 1: Clean raw data
8 | Sprint 1: Create test cases
9 | Sprint 1: Train models on tempreture finding
10 | Sprint 1: Implement initial threshold selection and initial detection algorithm
12 | Sprint 1: Test iniital prototype on three participants
13 | Sprint 1: Fix critical errors
14 | Sprint 1: Demonstrate initial protytype to supervisor
SPRINT 2
Task No | Task Name
14 | Sprint 2: Investigate errors introduced in Sprint 1
15 | Sprint 2: Investigate usability concerns expressed by participants
16 | Sprint 2: Update algorithm to fix errors
17 | Sprint 2: Update implementation to address usbability concerns
19 | Sprint 2: Extend models to differentiate between suitable and non suitable tempretures for user
23 | Sprint 2: Test final system on five participants
24 | Sprint 2: Calculate precision and recall
25 | Sprint 2: Demonstrate final system to supervisor and panel
26 | Sprint 2: Write project report
|  | week 1 (starting 27/08/2017) | Half of week 1 (starting 30/08/2017) | week 2 (starting 03/09/2017) | Half of week 2 (starting 06/09/2017) | week 3 (starting 10/09/2017) | Half of week 3 (starting 13/09/2017) | week 4 (starting 17/09/2017)